## Schedule
Task | Milestone? | Expected Duration | Actual Duration
Settle on project and approval by instructor | Y | 9/24 - 10/1 | 9/24 - 10/1
Finalize channel count on dev and relay boards |  | 10/1 - 10/5 | 10/1 - 10/5
Identify vendors for parts |  | 10/1 - 10/5 | 10/1 - 10/5
Prepare proposal |  | 10/5 - 10/6 | 10/5 - 10/6
Final instructor approval |  | 2013-10-08 | 2013-10-08
Finalize circuit design |  | 10/8 - 10/15 | 10/8 - 10/12
Order online parts (long-lead from China) | Y | 10/8 - 10/15 | 2013-10-12
Buy parts from store | Y | 10/8 - 10/15 | 2013-10-12
Pick song for display |  | 10/8-10/15 | 2013-10-13
Work on code for timing LEDs |  | 10/15 - 11/22
Relay board in hand |  | 2013-11-01
Build hardware setup | Y | 11/2 - 11/5
Lecture on ADC |  | 2013-11-05 | 2013-11-05
Write code to sync LEDs to song playback |  | 11/6 - 11/9
Change LEDs to look good with song (for nice video) |  | 11/22 - 11/28
Complete report | Y | 11/28 - 12/3
Project presentation | Y | 2013-12-04 | 2013-12-04